## YEAR 1 ACTIVITIES
MARDS, 1st year project flow with realisation chart
Activity status code (colours) |  |  |  |  | Ongoing | Partly Done | According to the plan | Done | Failed | Delayed | "X" activity in partner country |  | "=" activity in Program country |  |  | Need Action
WP, Actions, Deliverables | Titles | RESPONSIBLE PARTNER | INCLUDED PARTNER | STATUS | # WEEKS | MONTHS | [11 empty] | Note/Action | Reading in proposal document "MARDS part2 detailed description" | Temporary products
WP1/PRE | Monitoring and analysing of national systems and policies of doctoral education in Montenegro and Albania and comparing with EU practices |  | ALL |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp:83-85
A1.1 | Evaluation of the existing doctoral education policy and standards in Montenegro and Albania and comparing with EU practices | University of Zagreb (University of Vienna) | ALL | ONGOING | 16 | [12 empty] | Need action of the UNIZ and UNI Viena under assistance of Podgorica Skodra | bar: MONTHS M2 to MONTHS M5
A1.2 | Organization of a Conference on doctoral education in Montenegro and Albania | University of Zagreb (University of Vienna) | ALL | ACCORDING TO PLAN | 6 | bar: MONTHS M5 to MONTHS M7
A1.3 | Recommendations and purpose of basic legal documents on university and national levels | University of Zagreb (University of Vienna) | ALL | ACCORDING TO PLAN | 18 | bar: MONTHS M4 to MONTHS M12
Deliverables | [5 empty] | MONTHS M5: DEV1.1; MONTHS M7: DEV1.2; MONTHS M12: DEV1.3
WP2/DEV | Training of Montenegrin and Albanian academic staff and professionals/administration in doctoral education |  | ALL |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | PP:86-87
A2.1 | Training of academic and professional staff on EU practices of doctoral education | University of Banska Bystrica (University of Vienna) | ALL | ACCORDING TO PLAN | 20 | [12 empty] | Need action of Banska for prepearing mobility training plan | bar: M3 to DEV1.3 M12
A2.2 | Creating a Guidelines and recommendations for WB academics and professionals in doctoral studies | University of Banska Bystrica (University of Vienna) | ALL | ACCORDING TO PLAN | 4 | bar: DEV1.2 M11 to DEV1.3 M12
WP3/DEV | Establishing a new model of funding doctoral studies on national levels. |  | ALL |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp: 88-90
A3.1 | Evaluation of models for funding doctoral studies in Montenegro and Albania | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | ALL | ACCORDING TO PLAN | 8 | bar: M5 to M8
A3.2 | Adoption of bylaws on funding doctoral studies in Montenegro | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | ALL | ACCORDING TO PLAN | 20 | M8: 4X; M9: 2X2=; M10: 4X; =X M11: 4X; =X M12: 4X
A3.3 | Adoption of bylaws on funding doctoral studies in Albania | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | ALL | ACCORDING TO PLAN | 20 | M8: 4X; M9: 2X2=; M10: 4X; =X M11: 4X; =X M12: 4X
WP4/DEV | Establishment and start-up of Joint Pilot Doctoral Schools |  | ALL |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp:91-95
A4.1 | Development of the Curricula for joint Doctoral Schools | University of Montenegro (University of Shkodra) | ALL | ACCORDING TO PLAN | 8 | 4X M11: 2X2=; 4X M12: 2X2=
A4.2 | Equipping the laboratories and other infrastructure at partner universities | University of Montenegro (University of Shkodra) | ALL | ONGOING | 24 | [12 empty] | ASAP starting purchasing of equipment procedure where it is possible | bar: M2 to 4X M12
Deliverables | [5 empty] | 4X M12: DEV4.3
W5/QPLN | Quality plan |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp:96-99
A5.1 | Internal Quality Control | University of Maribor (University of Vienna) | ALL | ONGOING | 12 | [12 empty] | Need action, quality, plan strategy with plan Maribor, Vienna | bar: M2; M4; M6; M8; M10; DEV4.3 M12
A5.2 | External Quality Control | University of Maribor (University of Vienna) | ALL | ONGOING | 10 | [12 empty] | Need action, quality, plan strategy with plan Maribor, Vienna | bar: M3; M5; M7; M9; M11
Deliverables | [5 empty] | M3: D5.1
WP6/DISS EXP | Dissemination of the project |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp:100-103
A6.1 | Creation and updating project web site | University of Montenegro, UDG, under help of Metropolitan University Tirana and PRIDE network | ALL | ONGOING | 12 | [14 empty] | Web site installed Daily updated | bar: M1 to D5.1 M12
A6.2 | Creating and distribution of dissemination documents | University of Montenegro, UDG, under help of Metropolitan University Tirana and PRIDE network | ALL | ONGOING | 6 | [12 empty] | Need action in creating, Dissemination Material, UoM, Skodra | bar: M2; D5.1 M4; D5.1 M6; D5.1 M8 to D5.1 M12
Deliverables | [5 empty] | D5.1 M6: D6.1 D6.2 D6.3; D5.1 M12: D6.1 D6.2
WP7/DISS/EXP | Explotation and Sustainability of the project results |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp:104-106
A7.1 | Regular meetings about MARDS flow with stakeholders | Metropolitan University Tirana, Polytechnic Univerist of Tirana, Vlore Uni (under help of all) | ALL | ONGOING | 6 | bar: M2; M4; D6.1 D6.2 D6.3 M6; D6.1 D6.2 D6.3 M8 to D6.1 D6.2 D6.3 M9; D6.1 D6.2 D6.3 M11 to D6.1 D6.2 M12
A7.2 | Universities – stakeholders networking in Montenegro and Albania | Polytechnic University Tirana (under help of all) | ALL | ONGOING | 6 | bar: M4; D6.1 D6.2 D6.3 M6; D6.1 D6.2 D6.3 M8; D6.1 D6.2 D6.3 M11 to D6.1 D6.2 M12
Deliverables | [5 empty] | M4: D7.1
WP8/DISS/EXP | Management of the project |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp:107-111
A8.1 | Daily management of the project | University of Montenegro | ALL | ONGOING | 24 | [14 empty] | Daily management done, preparation activities Contracts, communication, local teams | bar: M1 to D7.1 M12
A8.2 | Precise guidelines for management of the project | University of Montenegro | ALL | ONGOING | 4 | [12 empty] | Need action by doing a rules for project managment | bar: M1 to M2
A8.3 | Regular meetings of project bodies | University of Montenegro | ALL | ONGOING | 3 | [12 empty] | Kick-off postponed | bar: M2; D7.1 M7; D7.1 M12
[8 empty] | D8.1 |  |  | D8.1
[7 empty] | D8.2 |  |  |  |  | D8.2 |  |  |  |  | D8.2
Note on H18: Radovan Stojanovic: Delayed
Note on I10: Radovan Stojanovic: Should be delayed and merged because of kick-off
Note on S10: Radovan Stojanovic: Should be delayed and merged because of kick-off
Note on S18: Radovan Stojanovic: Delayed

## DELIVERABLES
MARDS 's main delievrables (36) Months |  |  |  | 1st year
Delivarable # |  | Type | Month | Responsible | Expected Date
DE1.1 | Report on the “state of the art” in doctoral education in Montenegro and Albania and comparison with EU practices | Report | M5 | University of Zagreb (University of Vienna) | Mid April 2019
DE1.2 | Proceedings from conference about doctoral education in Montenegro and Albania | Report, Product | M7 | University of Zagreb (University of Vienna) | Mid June 2019
DE1.3 | Legal documents to be send to responsible bodies for adopting | Report | M12 |  | Mid Nov 2019
DE2.1 | Report on academic and professional training of WB staff/professionals/administrative' at EU | Report | M24 | University of Banska Bystrica (University of Vienna) | Mid Nov 2020
DE2.2 | Guidelines and recommendations for WB academics and professionals in doctoral studies | Teaching and training material | M24 | University of Banska Bystrica (University of Vienna) | Mid Nov 2020
DE3.1 | Report on appropriate funding doctoral studies in Montenegro and Albania | Report | M21 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | Mid Avg 2020
DE3.2 | Obligatory decision on adopting MARDS's methodology on funding for Montenegro | Decission | M28 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | Mid March 2021
DE3.2 | Obligatory decision on adopting MARDS's methodology on funding for Albania | Decission | M28 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | Mid March 2021
DE4.1 | Curricula book for Joint School suited in Albania (Shkoder) | Teaching, Learning and Training material | M18 | Univershity Shkoder and University of Montenegro | Mid June 2020
DE4.2 | Curricula book for Joint pilot school in Montenegro | Teaching, Learning and Training material | M18 | Univershity Shkoder and University of Montenegro | Mid June 2020
DE4.3 | The report on MARDS’s equipment resources | Report | M12 | Univershity Shkoder and University of Montenegro other Albanian Unis | Mid Nov 2020
DE4.4 | Final version of accreditation application | Report | M18 | Univershity Shkoder and University of Montenegro other Albanian Unis | Mid June 2020
DE4.5 | Decisions on accreditation | Decission | M20 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | Mid Avg 2020
DE4.6 | The list of enrolled students | List | M24 | University of Montenegro | Mid Nov 2020
DE5.1 | Quality Plan adopted | Report Service | M3 | University of Maribor University of Vienna | Mid Feb 2019
DE5.2 | Internal quality assurance reports delivered | Report | M36 | University of Maribor University of Vienna | Mid Nov 2021
DE5.3 | Tender for subtracting external QC experts completed | Service | M13 | University of Maribor University of Vienna | Mid Dec 2019
DE5.4 | External quality control and monitoring delivered | Report | M36 | External Experts | Mid Nov 2021
DE6.1 | Setting up and maintaining the project web site | Product | M1-M36 Every 6 months will be checked this deliverables | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE6.2 | Dissemination material created and distributed | Product | M1-M36 Every 6 months will be checked this deliverables | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE6.3 | Dissemination events with relevant stakeholders organised | Events | M6, M18, M24 | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE6.4 | MARDS doctorial Colloquium organised | Event | M35 | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network) | Mid Oct 2021
DE7.1 | Sustainability strategy adopted | Document | M4 | Metropolitan University Tirana (under help of UoM)
DE7.2 | University – Stakeholders network created | Product Servise | M36 | Metropolitan University Tirana (under help of UoM) | Mid Nov 2021
DE7.3 | Doctoral scholarships provided | Product | M23 | Metropolitan University Tirana (under help of UoM) | Mid Oct 2020
DE8.1 | Overall project management | All outputs | M1-M36 Every 3 months will be checked this deliverables | University of Montenegro
DE8.2 | Project coordination meetings | Events | M1-M36 Deliverable valid for sheduled meetings | University of Montenegro
DE8.3 | Periodical and Final reports | Reports | M18, M36 | University of Montenegro