## YEAR 1 ACTIVITIES
MARDS, 1st year project flow with realisation chart
Activity status code (colours) |  |  |  |  | Ongoing | Partly Done | According to the plan | Done | Failed | Delayed | "X" activity in partner country |  | "=" activity in Program country |  |  | Need Action
WP, Actions, Deliverables | Titles | RESPONSIBLE PARTNER | INCLUDED PARTNER | STATUS | # WEEKS | MONTHS | [11 empty] | Note/Action | Reading in proposal document "MARDS part2 detailed description" | Temporary products
WP1/PRE | Monitoring and analysing of national systems and policies of doctoral education in Montenegro and Albania and comparing with EU practices |  | ALL |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp:83-85
A1.1 | Evaluation of the existing doctoral education policy and standards in Montenegro and Albania and comparing with EU practices | University of Zagreb (University of Vienna) | ALL | ONGOING | 16 | [12 empty] | Need action of the UNIZ and UNI Viena under assistance of Podgorica Skodra | bar: MONTHS M2 to MONTHS M5
A1.2 | Organization of a Conference on doctoral education in Montenegro and Albania | University of Zagreb (University of Vienna) | ALL | ACCORDING TO PLAN | 6 | bar: MONTHS M5 to MONTHS M7
A1.3 | Recommendations and purpose of basic legal documents on university and national levels | University of Zagreb (University of Vienna) | ALL | ACCORDING TO PLAN | 18 | bar: MONTHS M4 to MONTHS M12
Deliverables | [5 empty] | MONTHS M5: DEV1.1; MONTHS M7: DEV1.2; MONTHS M12: DEV1.3
WP2/DEV | Training of Montenegrin and Albanian academic staff and professionals/administration in doctoral education |  | ALL |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | PP:86-87
A2.1 | Training of academic and professional staff on EU practices of doctoral education | University of Banska Bystrica (University of Vienna) | ALL | ACCORDING TO PLAN | 20 | [12 empty] | Need action of Banska for prepearing mobility training plan | bar: M3 to DEV1.3 M12
A2.2 | Creating a Guidelines and recommendations for WB academics and professionals in doctoral studies | University of Banska Bystrica (University of Vienna) | ALL | ACCORDING TO PLAN | 4 | bar: DEV1.2 M11 to DEV1.3 M12
WP3/DEV | Establishing a new model of funding doctoral studies on national levels. |  | ALL |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp: 88-90
A3.1 | Evaluation of models for funding doctoral studies in Montenegro and Albania | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | ALL | ACCORDING TO PLAN | 8 | bar: M5 to M8
A3.2 | Adoption of bylaws on funding doctoral studies in Montenegro | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | ALL | ACCORDING TO PLAN | 20 | M8: 4X; M9: 2X2=; M10: 4X; =X M11: 4X; =X M12: 4X
A3.3 | Adoption of bylaws on funding doctoral studies in Albania | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | ALL | ACCORDING TO PLAN | 20 | M8: 4X; M9: 2X2=; M10: 4X; =X M11: 4X; =X M12: 4X
WP4/DEV | Establishment and start-up of Joint Pilot Doctoral Schools |  | ALL |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp:91-95
A4.1 | Development of the Curricula for joint Doctoral Schools | University of Montenegro (University of Shkodra) | ALL | ACCORDING TO PLAN | 8 | 4X M11: 2X2=; 4X M12: 2X2=
A4.2 | Equipping the laboratories and other infrastructure at partner universities | University of Montenegro (University of Shkodra) | ALL | ONGOING | 24 | [12 empty] | ASAP starting purchasing of equipment procedure where it is possible | bar: M2 to 4X M12
Deliverables | [5 empty] | 4X M12: DEV4.3
W5/QPLN | Quality plan |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp:96-99
A5.1 | Internal Quality Control | University of Maribor (University of Vienna) | ALL | ONGOING | 12 | [12 empty] | Need action, quality, plan strategy with plan Maribor, Vienna | bar: M2; M4; M6; M8; M10; DEV4.3 M12
A5.2 | External Quality Control | University of Maribor (University of Vienna) | ALL | ONGOING | 10 | [12 empty] | Need action, quality, plan strategy with plan Maribor, Vienna | bar: M3; M5; M7; M9; M11
Deliverables | [5 empty] | M3: D5.1
WP6/DISS EXP | Dissemination of the project |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp:100-103
A6.1 | Creation and updating project web site | University of Montenegro, UDG, under help of Metropolitan University Tirana and PRIDE network | ALL | ONGOING | 12 | [14 empty] | Web site installed Daily updated | bar: M1 to D5.1 M12
A6.2 | Creating and distribution of dissemination documents | University of Montenegro, UDG, under help of Metropolitan University Tirana and PRIDE network | ALL | ONGOING | 6 | [12 empty] | Need action in creating, Dissemination Material, UoM, Skodra | bar: M2; D5.1 M4; D5.1 M6; D5.1 M8 to D5.1 M12
Deliverables | [5 empty] | D5.1 M6: D6.1 D6.2 D6.3; D5.1 M12: D6.1 D6.2
WP7/DISS/EXP | Explotation and Sustainability of the project results |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp:104-106
A7.1 | Regular meetings about MARDS flow with stakeholders | Metropolitan University Tirana, Polytechnic Univerist of Tirana, Vlore Uni (under help of all) | ALL | ONGOING | 6 | bar: M2; M4; D6.1 D6.2 D6.3 M6; D6.1 D6.2 D6.3 M8 to D6.1 D6.2 D6.3 M9; D6.1 D6.2 D6.3 M11 to D6.1 D6.2 M12
A7.2 | Universities – stakeholders networking in Montenegro and Albania | Polytechnic University Tirana (under help of all) | ALL | ONGOING | 6 | bar: M4; D6.1 D6.2 D6.3 M6; D6.1 D6.2 D6.3 M8; D6.1 D6.2 D6.3 M11 to D6.1 D6.2 M12
Deliverables | [5 empty] | M4: D7.1
WP8/DISS/EXP | Management of the project |  |  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |  | pp:107-111
A8.1 | Daily management of the project | University of Montenegro | ALL | ONGOING | 24 | [14 empty] | Daily management done, preparation activities Contracts, communication, local teams | bar: M1 to D7.1 M12
A8.2 | Precise guidelines for management of the project | University of Montenegro | ALL | ONGOING | 4 | [12 empty] | Need action by doing a rules for project managment | bar: M1 to M2
A8.3 | Regular meetings of project bodies | University of Montenegro | ALL | ONGOING | 3 | [12 empty] | Kick-off postponed | bar: M2; D7.1 M7; D7.1 M12
[8 empty] | D8.1 |  |  | D8.1
[7 empty] | D8.2 |  |  |  |  | D8.2 |  |  |  |  | D8.2
Note on H18: Radovan Stojanovic: Delayed
Note on I10: Radovan Stojanovic: Should be delayed and merged because of kick-off
Note on S10: Radovan Stojanovic: Should be delayed and merged because of kick-off
Note on S18: Radovan Stojanovic: Delayed

## DELIVERABLES
MARDS 's main delievrables (36) Months |  |  |  | 1st year
Delivarable # |  | Type | Month | Responsible | Expected Date
DE1.1 | Report on the “state of the art” in doctoral education in Montenegro and Albania and comparison with EU practices | Report | M5 | University of Zagreb (University of Vienna) | Mid April 2019
DE1.2 | Proceedings from conference about doctoral education in Montenegro and Albania | Report, Product | M7 | University of Zagreb (University of Vienna) | Mid June 2019
DE1.3 | Legal documents to be send to responsible bodies for adopting | Report | M12 |  | Mid Nov 2019
DE2.1 | Report on academic and professional training of WB staff/professionals/administrative' at EU | Report | M24 | University of Banska Bystrica (University of Vienna) | Mid Nov 2020
DE2.2 | Guidelines and recommendations for WB academics and professionals in doctoral studies | Teaching and training material | M24 | University of Banska Bystrica (University of Vienna) | Mid Nov 2020
DE3.1 | Report on appropriate funding doctoral studies in Montenegro and Albania | Report | M21 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | Mid Avg 2020
DE3.2 | Obligatory decision on adopting MARDS's methodology on funding for Montenegro | Decission | M28 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | Mid March 2021
DE3.2 | Obligatory decision on adopting MARDS's methodology on funding for Albania | Decission | M28 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | Mid March 2021
DE4.1 | Curricula book for Joint School suited in Albania (Shkoder) | Teaching, Learning and Training material | M18 | Univershity Shkoder and University of Montenegro | Mid June 2020
DE4.2 | Curricula book for Joint pilot school in Montenegro | Teaching, Learning and Training material | M18 | Univershity Shkoder and University of Montenegro | Mid June 2020
DE4.3 | The report on MARDS’s equipment resources | Report | M12 | Univershity Shkoder and University of Montenegro other Albanian Unis | Mid Nov 2020
DE4.4 | Final version of accreditation application | Report | M18 | Univershity Shkoder and University of Montenegro other Albanian Unis | Mid June 2020
DE4.5 | Decisions on accreditation | Decission | M20 | Ministries of education of Montenegro and Albania (under assistance of Ministries of Sciences). | Mid Avg 2020
DE4.6 | The list of enrolled students | List | M24 | University of Montenegro | Mid Nov 2020
DE5.1 | Quality Plan adopted | Report Service | M3 | University of Maribor University of Vienna | Mid Feb 2019
DE5.2 | Internal quality assurance reports delivered | Report | M36 | University of Maribor University of Vienna | Mid Nov 2021
DE5.3 | Tender for subtracting external QC experts completed | Service | M13 | University of Maribor University of Vienna | Mid Dec 2019
DE5.4 | External quality control and monitoring delivered | Report | M36 | External Experts | Mid Nov 2021
DE6.1 | Setting up and maintaining the project web site | Product | M1-M36 Every 6 months will be checked this deliverables | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE6.2 | Dissemination material created and distributed | Product | M1-M36 Every 6 months will be checked this deliverables | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE6.3 | Dissemination events with relevant stakeholders organised | Events | M6, M18, M24 | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network)
DE6.4 | MARDS doctorial Colloquium organised | Event | M35 | Metropolitan University Tirana (under help of University of Montenegro and PRIDE network) | Mid Oct 2021
DE7.1 | Sustainability strategy adopted | Document | M4 | Metropolitan University Tirana (under help of UoM)
DE7.2 | University – Stakeholders network created | Product Servise | M36 | Metropolitan University Tirana (under help of UoM) | Mid Nov 2021
DE7.3 | Doctoral scholarships provided | Product | M23 | Metropolitan University Tirana (under help of UoM) | Mid Oct 2020
DE8.1 | Overall project management | All outputs | M1-M36 Every 3 months will be checked this deliverables | University of Montenegro
DE8.2 | Project coordination meetings | Events | M1-M36 Deliverable valid for sheduled meetings | University of Montenegro
DE8.3 | Periodical and Final reports | Reports | M18, M36 | University of Montenegro

## Sheet3
MARDS 2nd YEAR TRACKER
WP3 DEV | Establishing a new model of funding doctoral studies on national levels | M1 | M2 | M3 | M4 | M5
A3.2 | Adoption of bylaws on funding doctoral studies in Montenegro
A3.3 | Adoption of bylaws on funding doctoral studies in Albania
DEV3.2,3.3
Decision on adopting MARDS's methodology on funding for Montenegro and Albania and First Scholarships Given
Ministries in AL and ME
WP4/DEV | Establishment and start-up of Joint Pilot Doctoral Schools | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
A4.1 | Development of the Curricula for joint Doctoral Schools | bar: M1 to Ministries in AL and ME M6
A4.2 | Accreditation of the Doctoral Schools | bar: Ministries in AL and ME M6 to Ministries in AL and ME M9
A4.3 | Enrolling the first generation | Ministries in AL and ME M6: D4.1,4.2; Ministries in AL and ME M9: D4.4.4, 4.5
[7 empty] | Curricula Book |  |  | Decision on accreditaion |  |  | D4.6
The list of the enroled students
[7 empty] | (Shkodra, Vlore, PUT, Podgorica, UDG) |  |  | Ministries Shkodra Podgorica |  |  | All partners
[7 empty] | D4.3 | [5 empty] | Podgorica, UDG, Vlore, Shkodra, PUT
Final Version of Application Ministries
Ministries, Shkodra, Podgorica, UDG
WP5QPL | QUALITY PLAN | M1: M1; M2: M2; M3: M3
A5.4 | External quality control and monitoring delivered | bar: M1 to M3
D5.2
Two experts from non-participating EU institutions will be engaged (subcontracted) as external evaluators according the international tender. The tender will define Terms of References (TOR) for such kind of job and it will be initiated from beginning of second year (M13) and completed by M16. TOR and Tender will be prepared by QMC, while announced by SC
Maribor
WP6: | Dissemination | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
A6.1 | Creation and updating project web site | [12 empty] | Metropolitan/PRIDE
A6.2 | Creating and distribution of dissemination documents | [12 empty] | Metropolitan/PRIDE
A6.3 | Organizing dissemination conference with stakeholders
DE6.3
Metropoliten
WP7: DISS/EXP | Explotation and Sustainability of the project results | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
A7.1 | Regular meetings about MARDS flow with stakeholders | [12 empty] | Metropolitab
A7.2 | Universities – stakeholders networking in Montenegro and Albania | [12 empty] | Chambers
A7.3 | Establishment of sustainable scholarships in Albania and Montenegro | [12 empty] | UDG/METROPOLITAN
A7.4 | Promotion of Doctoral School in Region | [12 empty] | UDG/METROPOLITAN/Chambers
WP8: MNGT | Management | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | University of Montenegro
ZAGREB, VIENNA TO PUSH THE PROCESS WITH ACCREDITATION AND PhD